## Project2
Item Number | Goal | Task | Estimated Time | Assigned To | Target Deadline | Actual Time | Actual Delivery | Status | Comments
0 | Learning JavaFX | Walkthrough pdf provided by Drew | 5 | Everyone | 2022-03-23 | 7
1 | Minimal Working System |  | 10 |  |  | 10
1.1 |  | There will be a server and a graphical (old: text-based) client. |  | Zy | 2022-03-24 |  |  | Completed
1.2 |  | The server must support multiple games at a time. | 1 | JJ | 2022-03-24 | 3 |  | Completed
1.3 |  | A player should have a login + password so they can return to their games | 5 | Ch | 2022-03-24 | 4 |  | Completed
1.4 |  | The server should allow a player to be a member of multiple games at a time. | 1 | Jerry | 2022-03-24 |  |  | Completed
1.5 |  | Refactor and cleanup code | 3 | Ch | 2022-03-24 | 3 |  | Completed
2 | Multiple Players/Multiple Territories |  | 15.5 |  |  | 12.5
2.1 |  | Graphically display which territories are connected to which other territories | 2.5 | Jerry | 2022-03-26 | 3.5 |  | Completed
2.2 |  | Graphically display which player currently owns a given territory | 2.5 | Zy | 2022-03-26 | 3 |  | Completed
2.3 |  | Graphically display how many units of each type are in each territory | 1.5 | JJ | 2022-03-26 | 1 |  | Completed
2.4 |  | Graphically display which type(s)/amount(s) of resource each territory produces | 2 | Ch | 2022-03-26 | 2 |  | Completed
2.5 |  | Graphically display the "size" of the territory (this is a new attribute that reflects the cost to move through the territory) | 4 | Jerry | 2022-03-26 |  |  | Completed
2.6 |  | Refactor and cleanup code | 3 | Everyone | 2022-03-26 | 3 |  | Completed
3 | Units in Territories |  | 8 |  |  | 9.5
3.1 |  | Each player shall pick (or be assigned) one such group as her starting territories. Each player's starting territory set should have the same resource production as all other players' starting territory sets). | 2 | Jerry | 2022-03-28 | 3 |  | Completed
3.2 |  | Each player shall have the same number of initial units, which she may place in her territories as she wishes. These shall all be "basic" units. | 1 | JJ | 2022-03-28 | 2 |  | Completed
3.3 |  | Each territory now also has a "size" which represent the cost to move through it. The total size of territories should also be equivalent between players in the initial territory groupings. | 2 | Zy | 2022-03-28 | 1.5 |  | Completed
3.4 |  | Refactor and cleanup code | 3 | Everyone | 2022-03-28 | 3 |  | Completed
4 | Move Orders |  | 19.5 |  |  | 21
4.1 |  | There are three (old: two) types of orders that a player may issue: upgrade, move and attack (more below). | 2 | Zy | 2022-04-02 | 6 |  | Completed
4.2 |  | Each move order now consumes "food" resources. Speci cally, the cost of each move is (total size of territories moved through) * (number of units moved). | 2.5 | Ch | 2022-04-02 | 1.5 |  | Completed
4.3 |  | The game must pick the minimum total cost valid path when determining the cost. | 2 | Ch | 2022-04-02 | 4 |  | Completed
4.4 |  | An attack order now costs 1 food per unit attacking. | 1.5 | JJ | 2022-04-02 | 0.5 |  | Completed
4.5 |  | Receive new units: At the end of each turn, one new basic unit shall appear in each territory. | 1.5 | Zy | 2022-04-02 | 0.5 |  | Completed
4.6 |  | The player shall also increase their resource totals by adding the resource production of each territory that they own at the end of the turn. Note that this means that they get credit for any territories won in that turn. | 4 | Jerry | 2022-04-02 | 2 |  | Completed
4.7 |  | Client interface to commit move orders and end turn | 3 | JJ | 2022-04-02 | 3.5 |  | Completed
4.8 |  | Refactor and cleanup code | 3 | Everyone | 2022-04-02 | 3 |  | Completed
5 | Attack Orders |  | 8.5 |  |  | 6.5
5.1 |  | The server rolls two 20-sided dice (one for the attacker, one for the defender). Each roll is modi fied by adding a bonus for the type of unit involved. (Shown in the table on the next page) | 2 | Jerry | 2022-04-03 | 1.5 |  | Completed
5.2 |  | The order of evaluation alternates between the highest-bonus attacker unit paired with the lowest-bonus defender unit, and the lowest-bonus attacker unit paired with the highest-bonus defender unit. | 3.5 | Zy | 2022-04-03 | 2 |  | Completed
5.3 |  | Refactor and cleanup code | 3 | Everyone | 2022-04-03 | 3 |  | Completed
7 | Upgrade |  | 13 |  |  | 16.5
7.1 |  | Each player shall have a "maximum technology level" which starts at 1. | 1 | Jerry | 2022-04-05 | 1 |  | Completed
7.2 |  | Each player may issue an upgrade order to increase their maximum technology level. | 1 | JJ | 2022-04-05 | 2 |  | Completed
7.3 |  | The maximum technology level can only be upgraded by one step each turn. | 1 | Zy | 2022-04-05 | 0.5 |  | Completed
7.4 |  | A player may issue any number of upgrade orders to upgrade the units they have. | 3 | Ch | 2022-04-05 | 4.5 |  | Completed
7.5 |  | A player can upgrade any unit to any other unit type by paying the difference in totalcost, in a single upgrade order. | 5 | JJ | 2022-04-05 | 4 |  | Completed
7.6 |  | A player can only upgrade to units of types permitted by their maximum technology level | 2 | Ch | 2022-04-05 | 1.5 |  | Completed
7.7 |  | Refactor and cleanup code | 3 | Everyone | 2022-04-05 | 3 |  | Completed
Grade List
• Your project planning/project management.
• Your prototype of attack orders + discussion of it.
• Inclusion of the UX principles.
• Functionality
• Design
• Documentation, including explanations of your applications of the UX principles.
• Testing
• Other Code Quality Factors (e.g., naming, formatting, smells).
• Process (Issue tracking, CI/CD, Code Reviews, etc).

## Project1
Item Number | Goal | Task | Estimated Time | Assigned To | Target Deadline | Actual Time | Actual Delivery | Status | Comments
1 | Minimal Working System |  | 7.5 |  |  | 11
1.1 |  | Minimal Territory Class (only name) | 0.5 | Jerry | 2022-02-25 | 0.5 |  | Completed
1.2 |  | Minimal Map Class (only 1 Territory) | 0.5 | Zy | 2022-02-25 | 0.5 |  | Completed
1.3 |  | Client: display map + exit | 2 | JJ | 2022-02-25 | 1 |  | Completed
1.4 |  | Server: makes 1 territory map, sends to 1 client | 1 | Ch | 2022-02-25 | 4 |  | Completed
1.5 |  | Setup CI/CD, including automated tests | 2 | Jerry | 2022-02-25 | 2 |  | Completed
1.6 |  | Parse File | 1.5 | Zy | 2022-02-25 | 3 |  | Completed
2 | Multiple Players/Multiple Territories |  | 12 |  |  | 24
2.1 |  | Map supports more than one territory | 1 | Zy | 2022-03-01 | 2 |  | Completed
2.2 |  | Server supports connections from multiple clients | 1 | JJ | 2022-03-01 | 2 |  | Completed | Groups of 3 only have to support 2 players
2.3 |  | Client identifies which player (red, green, blue) | 1 | Ch | 2022-03-01 | 2.5 |  | Completed
2.4 |  | Each territory owned by a player | 1 | Jerry | 2022-03-01 | 2 |  | Completed
2.5 |  | Client displays territories grouped by owner | 1.5 | Ch | 2022-03-01 | 3.5 |  | Completed
2.6 |  | Add adjacency information to territories | 1 | Jerry | 2022-03-01 | 2 |  | Completed
2.7 |  | Client displays adjacency information | 1 | JJ | 2022-03-01 | 2.5 |  | Completed
2.8 |  | Make one or more interesting maps | 1.5 | Zy | 2022-03-01 | 3 |  | Completed
2.9 |  | Refactor and cleanup code | 3 | Everyone | 2022-03-01 | 4.5 |  | Completed
3 | Units in Territories |  | 13 |  |  | 15
3.1 |  | Each territory holds units | 0.5 | Zy | 2022-03-06 | 1 |  | Completed
3.2 |  | Client displays unit information for each territory | 0.5 | Ch | 2022-03-06 | 1.5 |  | Completed
3.3 |  | Server provides groups of territories to start in | 2 | Ch | 2022-03-06 | 3.5 |  | Completed | Groups of 3 can just provide fixed starting map
3.4 |  | Assignment of or choosing of territory groups to start | 1 | JJ | 2022-03-06 | 1.5 |  | Completed | Groups of 3 can just provide fixed starting map
3.5 |  | Server support for initial unit placement | 1.5 | Zy | 2022-03-06 | 2 |  | Completed | Groups of 3 can just provide fixed starting map
3.6 |  | Client support for initial unit placement | 1.5 | Jerry | 2022-03-06 | 1.5 |  | Completed | Groups of 3 can just provide fixed starting map
3.7 |  | Server indicates to all clients when placement phase done | 3 | JJ | 2022-03-06 | 2 |  | Completed | Groups of 3 can just provide fixed starting map
3.8 |  | Refactor and cleanup code | 3 | Everyone | 2022-03-06 | 2 |  | Completed
4 | Move Orders |  | 15 |  |  | 19.5
4.1 |  | Server supports move order (no error checking, one per client per turn) | 1.5 | JJ | 2022-03-11 | 3 |  | Completed
4.2 |  | Client supports entry + sending of move order | 1.5 | Jerry | 2022-03-11 | 2 |  | Completed
4.3 |  | Server error checks for move orders: ownership/number of units | 2 | Zy | 2022-03-11 | 2 |  | Completed
4.4 |  | Server error checking for move orders: path exists | 2 | Jerry | 2022-03-11 | 1 |  | Completed
4.5 |  | (optional) client validation of move order before sending | 1 | Zy | 2022-03-11 | 2 |  | Completed
4.6 |  | Server supports multiple move orders per turn, with "commit" | 2 | Ch | 2022-03-11 | 3.5 |  | Completed
4.7 |  | Client interface to commit move orders and end turn | 2 | JJ | 2022-03-11 | 4 |  | Completed
4.8 |  | Refactor and cleanup code | 3 | Everyone | 2022-03-11 | 2 |  | Completed
5 | Attack Orders |  | 17.5 |  |  | 19
5.1 |  | Server can receive (but not yet resolve) attack orders | 0.5 | Ch | 2022-03-15 | 1 |  | Completed
5.2 |  | Client support to send attack orders | 0.5 | JJ | 2022-03-15 | 1.5 |  | Completed
5.3 |  | Server resolves "simple" attacks | 2 | Zy | 2022-03-15 | 1 |  | Completed
5.4 |  | Server resolves mulltiple attackers into one territory | 3.5 | Ch | 2022-03-15 | 5 |  | Completed
5.5 |  | Units moving into a territory defend it | 2 | JJ | 2022-03-15 | 1 |  | Completed
5.6 |  | Units moving out of a territory do not defend it | 1.5 | Ch | 2022-03-15 | 1.5 |  | Completed
5.7 |  | (optional) client validation for attack orders before sending | 2.5 | Jerry | 2022-03-15 | 2 |  | Completed
5.8 |  | Special condition | 2 | Zy | 2022-03-15 | 3 |  | Completed
5.9 |  | Refactor and cleanup code | 3 | Everyone | 2022-03-15 | 3 |  | Completed
6 | Victory and Defeat |  | 14.5 |  |  | 20
6.1 |  | Server detects when a player has lost | 2 | Zy | 2022-03-18 | 2 |  | Completed
6.2 |  | Server automatically commits empty set of moves for players who lost | 2.5 | Ch | 2022-03-18 | 4 |  | Completed | Groups of 3 do not need: only 2 players
6.3 |  | Ensure disconnection of players works ok | 3 | JJ | 2022-03-18 | 5 |  | Completed | Groups of 3 do not need: only 2 players
6.4 |  | Ensure players who have lost may watch game | 3 | JJ | 2022-03-18 | 2 |  | Completed | Groups of 3 do not need: only 2 players
6.5 |  | Server detects when a player wins, notifies clients | 2 | Jerry | 2022-03-18 | 2 |  | Completed | For groups of 3, this is the same as 6.1
6.6 |  | Clients display win information and exit | 2 | Ch | 2022-03-18 | 2 |  | Completed
6.7 |  | Refactor and cleanup code | 3 | Everyone | 2022-03-18 | 3 |  | Completed

## Statuses
Unassigned
Assigned
Started
Testing
Code Review
Completed