## Sheet1
Item Number | Goal | Task | Estimated Time | Assigned To | Target Deadline | Actual Time | Actual Delivery | Status | Comments
1 | Minimal Working System |  | 7.5 |  |  | 11
1.1 |  | Minimal Territory Class (only name) | 0.5 | Jerry | 2022-02-25 | 0.5 |  | Completed
1.2 |  | Minimal Map Class (only 1 Territory) | 0.5 | Zy | 2022-02-25 | 0.5 |  | Completed
1.3 |  | Client: display map + exit | 2 | JJ | 2022-02-25 | 1 |  | Completed
1.4 |  | Server: makes 1 territory map, sends to 1 client | 1 | Ch | 2022-02-25 | 4 |  | Completed
1.5 |  | Setup CI/CD, including automated tests | 2 | Jerry | 2022-02-25 | 2 |  | Completed
1.6 |  | Parse File | 1.5 | Zy | 2022-02-25 | 3 |  | Completed
2 | Multiple Players/Multiple Territories |  | 12 |  |  | 24
2.1 |  | Map supports more than one territory | 1 | Zy | 2022-03-01 | 2 |  | Completed
2.2 |  | Server supports connections from multiple clients | 1 | JJ | 2022-03-01 | 2 |  | Completed | Groups of 3 only have to support 2 players
2.3 |  | Client identifies which player (red, green, blue) | 1 | Ch | 2022-03-01 | 2.5 |  | Completed
2.4 |  | Each territory owned by a player | 1 | Jerry | 2022-03-01 | 2 |  | Completed
2.5 |  | Client displays territories grouped by owner | 1.5 | Ch | 2022-03-01 | 3.5 |  | Completed
2.6 |  | Add adjacency information to territories | 1 | Jerry | 2022-03-01 | 2 |  | Completed
2.7 |  | Client displays adjacency information | 1 | JJ | 2022-03-01 | 2.5 |  | Completed
2.8 |  | Make one or more interesting maps | 1.5 | Zy | 2022-03-01 | 3 |  | Completed
2.9 |  | Refactor and cleanup code | 3 | Everyone | 2022-03-01 | 4.5 |  | Completed
3 | Units in Territories |  | 13 |  |  | 15
3.1 |  | Each territory holds units | 0.5 | Zy | 2022-03-06 | 1 |  | Completed
3.2 |  | Client displays unit information for each territory | 0.5 | Ch | 2022-03-06 | 1.5 |  | Completed
3.3 |  | Server provides groups of territories to start in | 2 | Ch | 2022-03-06 | 3.5 |  | Completed | Groups of 3 can just provide fixed starting map
3.4 |  | Assignment of or choosing of territory groups to start | 1 | JJ | 2022-03-06 | 1.5 |  | Completed | Groups of 3 can just provide fixed starting map
3.5 |  | Server support for initial unit placement | 1.5 | Zy | 2022-03-06 | 2 |  | Completed | Groups of 3 can just provide fixed starting map
3.6 |  | Client support for initial unit placement | 1.5 | Jerry | 2022-03-06 | 1.5 |  | Completed | Groups of 3 can just provide fixed starting map
3.7 |  | Server indicates to all clients when placement phase done | 3 | JJ | 2022-03-06 | 2 |  | Completed | Groups of 3 can just provide fixed starting map
3.8 |  | Refactor and cleanup code | 3 | Everyone | 2022-03-06 | 2 |  | Completed
4 | Move Orders |  | 15 |  |  | 19.5
4.1 |  | Server supports move order (no error checking, one per client per turn) | 1.5 | JJ | 2022-03-11 | 3 |  | Completed
4.2 |  | Client supports entry + sending of move order | 1.5 | Jerry | 2022-03-11 | 2 |  | Completed
4.3 |  | Server error checks for move orders: ownership/number of units | 2 | Zy | 2022-03-11 | 2 |  | Completed
4.4 |  | Server error checking for move orders: path exists | 2 | Jerry | 2022-03-11 | 1 |  | Completed
4.5 |  | (optional) client validation of move order before sending | 1 | Zy | 2022-03-11 | 2 |  | Completed
4.6 |  | Server supports multiple move orders per turn, with "commit" | 2 | Ch | 2022-03-11 | 3.5 |  | Completed
4.7 |  | Client interface to commit move orders and end turn | 2 | JJ | 2022-03-11 | 4 |  | Completed
4.8 |  | Refactor and cleanup code | 3 | Everyone | 2022-03-11 | 2 |  | Completed
5 | Attack Orders |  | 17.5 |  |  | 19
5.1 |  | Server can receive (but not yet resolve) attack orders | 0.5 | Ch | 2022-03-15 | 1 |  | Completed
5.2 |  | Client support to send attack orders | 0.5 | JJ | 2022-03-15 | 1.5 |  | Completed
5.3 |  | Server resolves "simple" attacks | 2 | Zy | 2022-03-15 | 1 |  | Completed
5.4 |  | Server resolves mulltiple attackers into one territory | 3.5 | Ch | 2022-03-15 | 5 |  | Completed
5.5 |  | Units moving into a territory defend it | 2 | JJ | 2022-03-15 | 1 |  | Completed
5.6 |  | Units moving out of a territory do not defend it | 1.5 | Ch | 2022-03-15 | 1.5 |  | Completed
5.7 |  | (optional) client validation for attack orders before sending | 2.5 | Jerry | 2022-03-15 | 2 |  | Completed
5.8 |  | Special condition | 2 | Zy | 2022-03-15 | 3 |  | Completed
5.9 |  | Refactor and cleanup code | 3 | Everyone | 2022-03-15 | 3 |  | Completed
6 | Victory and Defeat |  | 14.5 |  |  | 20
6.1 |  | Server detects when a player has lost | 2 | Zy | 2022-03-18 | 2 |  | Completed
6.2 |  | Server automatically commits empty set of moves for players who lost | 2.5 | Ch | 2022-03-18 | 4 |  | Completed | Groups of 3 do not need: only 2 players
6.3 |  | Ensure disconnection of players works ok | 3 | JJ | 2022-03-18 | 5 |  | Completed | Groups of 3 do not need: only 2 players
6.4 |  | Ensure players who have lost may watch game | 3 | JJ | 2022-03-18 | 2 |  | Completed | Groups of 3 do not need: only 2 players
6.5 |  | Server detects when a player wins, notifies clients | 2 | Jerry | 2022-03-18 | 2 |  | Completed | For groups of 3, this is the same as 6.1
6.6 |  | Clients display win information and exit | 2 | Ch | 2022-03-18 | 2 |  | Completed
6.7 |  | Refactor and cleanup code | 3 | Everyone | 2022-03-18 | 3 |  | Completed

## Statuses
Unassigned
Assigned
Started
Testing
Code Review
Completed